## Sprint1
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART (Team 1)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
1. As a student I want to see all the subject in the SD Course with their short description so that I can see all the subjects of SD course in each semester separately | 13 |  | Done
Create a web page |  | MOHIT | Done | 10 | 10 | 0 | 0 | 0 | 0 | 0
Display all the subjects of SD course in each semester seperately |  | ADITYA | Done | 30 | 10 | 10 | 0 | 10 | 0 | 0
describe short detail about all the course subject seperately |  | ASHFAK | Done | 40 | 10 | 10 | 0 | 10 | 10 | 0
put all information in tabular form |  | AYUSH | Done | 40 | 10 | 10 | 10 | 0 | 10 | 0
2. As a student I want all the faculty details page so that I can see each faculty name along with their photo, skills, area of expertise | 13 |  | Done
Create a new web page |  | RUCHI | Done | 10 | 10 | 0 | 0 | 0 | 0 | 0
display the images, skills and area of expertise of faculty members |  | ASHFAK | Done | 40 | 0 | 10 | 10 | 10 | 10 | 0
put all information in tabular form |  | TANMOY | Done | 50 | 10 | 10 | 10 | 10 | 10 | 0
Task
3 As a student I want grading criteria system so that I can come to know about the grading criteria of SD course | 13 |  | Done
Create a new web page |  | ADITYA | Done | 10 | 0 | 10 | 0 | 0 | 0 | 0
describe the grading criteria of SD course |  | MOHIT | Done | 50 | 10 | 10 | 10 | 10 | 10 | 0
Task
Task
TOTAL |  |  |  | 280 | 70 | 70 | 40 | 50 | 50 | 0

## Sprint2
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
4. As a student I want FAQ option in the webpage so that I can ask about the queries related to this course | 40
Create a new web page |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0
Make an enquiry form |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
make an interactive chat option |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0
Add some default question |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Connect to email |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
5 As a Student I want gallery page so that I can see the images like all the events photos, group photos, achievement photos. | 13
craete a new web page |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0
Add photos |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0
All the images are in slide show format |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Use animation |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0
User Stories#3
Task
Task
Task
Task
TOTAL |  |  |  | 270 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 3
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
6. As a student I want some major project details with a short description so that I can see the different major project of difference subject along with their image or video and also the project creator and faculty who guided the projects | 40
Create a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add some project detail in images or video format |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Add some description about the project |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0
7 As a Student I want testimonials slide so that I can see the name, image and testimonials of SD faculty and students | 13
craete a new web page |  |  |  | 10 | 0 | 1 | 1 | 0 | 0 | 0
Add photos , names |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
All the images are in slide show format |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Use animation |  |  |  | 40 | 0 | 0 | 0 | 0 | 1 | 0
8. As a student I want CGPA Calculator so that I can enter my marks and calculate the CGPA.
create a new page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
create a form to accept marks |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
make a calculator |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
write js code |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 280 | 0 | 1 | 1 | 0 | 1 | 0

## Sprint 4
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
9. As a student I want admission inquiry page so that I can see the admission page consisting a form to apply for admission in SD only | 40
Create a new web page |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0
Add documentation details |  |  |  | 25 | 0 | 0 | 0 | 0 | 0 | 0
Connect to mail |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Add admission details |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
10 As a Student I want mentor/ mentee detail so that I can see the list of mentor or mentee of each semester and their names. | 13
create a new web page |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0
Add details about mentor/ mentee |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
add option for query |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
connect to mail |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
11.As a Student I want an appointment page so that I can request for an appointment to the Sd faculty through mail
create a new web page |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0
Add option for appointment |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
connect to mail |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 280 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 5
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
12. As a student I want events page where I can see the events held so that i can see the different major events of SD course along with their image or video and also the event details such as hosted by, location and faculty who guided the event. | 40
Create a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add images or video |  |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0
Add event details |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0
Add a form to request for hosting an event |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
connect to mail |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
13. As a Student I want self assessment page so that I can check my knowledge in different subjects through some basic MCQ of 12th standard and some Technical/General knowledge based questions | 13
craete a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add subjects |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Add quiz in google form |  |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3
Task
Task
Task
Task
TOTAL |  |  |  | 280 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 6
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
14. As a student I want to know about the laptop requirements so that I can know the minimum laptop requirements along with some suggestions of laptops we might like to buy. | 40
Create a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add laptop detail |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0
Add link to buy laptop |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0
Add some suggestion |  |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0
15 As a student I want Calendar so that I can see the list of all the events and holidays | 13
craete a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add calendar |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0
Add upcoming holiday and events |  |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3
Task
Task
Task
Task
TOTAL |  |  |  | 280 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 7
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
16. As a student I want a feedback form so that I can give comment or feedback and which will be mailed to all faculty members | 40
Create a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add a feedback form |  |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0
connect to mail |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0
Give rating option |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0
17 As a Student I want all the companies name that hires the student of Sd course so that I can come to know the name of all the majoy IT companies that often comes to offer internship | 13
craete a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add companies logo |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Add company link |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Add placed student photos |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3
Task
Task
Task
Task
TOTAL |  |  |  | 280 | 0 | 0 | 0 | 0 | 0 | 0