## Version1
Product Backlog
ID | As a | I want … | So that… | Notes | Developer Name | Estimation (Story Points) | Priority | Sprint | Access crieteria | Acceptance Criteria | Demo | Status
1 | Student | to see all the subject in the SD Course with their short description | I can see all the subjects of SD course in each semester separately | New page containing a table | Mohit, Ayush, Aditya, Ashfak | 13 | Medium | Sprint 1 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | Shows all the subjects of SD course in each semester seperately | Done
2 | Student | all the faculty details page | I can see each faculty name along with their photo, skills, area of expertise | Landing page with multiple new pages linked | Ruchi, Tanmoy, Ashfak, Tanmoy | 13 | Medium | Sprint 1 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will take to another page where each faculty name along with their photo, qualification, area of experties and also a button to request for an appointment will be added in a card for each faculty | Done
3 | Student | FAQ option in the webpage | I can ask about the queries related to this course | New page with some old pages linked | Aditya, Ruchi, Ashfak | 40 | High | Sprint 2 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will lead to a page asking with lots of questions about what kind of quairy () and then will be guided to the respective page. (Example "how must you need to pay?")( If their enquiry is not charted then their question will be for warded to the concerned authority through mail) | Done
4 | Student | some major project details with a short description | I can see the different major project of difference subject along with their image or video and also the project creator and faculty who guided the projects | New page linked with different YouTube vidoes | Ayush, Tanmoy | 21 | Medium | Sprint 3 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will take you to a page where different major project of difference subject will be visible along with their image or video and also the project creator and faculty who guided the projects | Not Done
5 | Student | events page where I can see the events held | i can see the different major events of SD course along with their image or video and also the event details such as hosted by, location and faculty who guided the event. | New page linked with different vidoes and images | TBA | 21 | Medium | Sprint 5 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will take you to a page where different major events of SD course will be visible along with their image or video and also the event details such as hosted by, location and faculty who guided the event. Event a request form will be available to email the HOD requesting to hosting an events | Not Done
6 | Student | testimonial slides | I can see the name, image and testimonials of SD faculty and students | Landing page at the bottom like a slideshow | Tanmoy, Ruchi, Aditya | 21 | High | Sprint 3 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | A slide show consisting of slides including name, image and testimonils of SD faculty and students | Not Done
7 | Student | Gallery page | I can see the images like all the events photos, group photos, achievement photos. | New page linked with multiple images | Mohit, Tanmoy, Ayush | 40 | High | Sprint 2 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | it will lead to a page filled with only the images like all the events photos, group photos, achievement photos, and will again lead to different pges consisting images of the selected event | Done
8 | Student | to know about the laptop requirements | I can know the minimum laptop requirements along with some suggestions of laptops we might like to buy. | New Page linked with other websites | TBA | 8 | Medium | Sprint 6 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will take to a page consisting the minimum laptop requirements along with some suggestions of lapotops they might like to buy. That will be linked with online marketing websites like Amazon and Flipkart | Not Done
9 | Student | all the companies name that hires the student of Sd course | I can come to know the name of all the majoy IT companies that often comes to offer internship | New Page linked with other websites | TBA | 8 | Medium | Sprint 7 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will lead to a page with logo and name of all the majoy IT companies that often comes to offer internship and they will be linked with their official company website. | Not Done
10 | Student | an appointment page | I can request for an appointment to the Sd faculty through mail | New page consisting of old links | TBA | 21 | High | Sprint 4 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will take to another page where each faculty name along with their photo, qualification, area of experties and also a button to request for an appointment will be added in a card for each faculty | Not Done
11 | Student | a feedback form | I can give comment or feedback and which will be mailed to all faculty members | Landing page bottom and will be linked with all the other pages | TBA | 21 | Medium | Sprint 7 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | A form asking for comment or feedback and will be mailed to all faculty members and to students who made this website. | Not Done
12 | Student | self assessment page | I can check my knowledge in different subjects through some basic MCQ of 12th standard and some Technical/General knowledge based questions. | New pages leading to multiple google forms | TBA | 40 | High | Sprint 5 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | Any with thrust for knowledge will be given options of subjects and will turn to a google form asking several basic MCQ of 12th standard and some Technical/General knowledge based questions. | Not Done
13 | Student | grading criteria system | I can come to know about the grading criteria of SD course | New page consisting table | Mohit | 13 | Medium | Sprint 1 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will take to a page consisting table on how and on the basis of what a SD student is being graded and along with the unique grading system of SD. | Done
14 | Student | GPA Calculator | I can enter my marks and calculate the CGPA. | New page with a calculator | Mohit, Ruchi, Ashfak | 40 | High | Sprint 3 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will lead to a page which will accepts the grades and credit points And calculaet your efforts. | Not Done
15 | Student | a calendar | I can see the list of all the events and holidays | New page with a calender | TBA | 13 | Medium | Sprint 6 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will lead to a calender page showing upcoming events as well as list of all the events | Not Done
16 | Student | mentor/ mentee detail | I can see the list of mentor or mentee of each semester and their names. | Landing page and a new page | TBA | 21 | Medium | Sprint 4 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | Landing page will consist the introduction and will be linked to new page consisting list of mentor or mentee of each semester and their names. | Not Done
17 | Student | admission inquiry page | I can see the admission page consisting a form to apply for admission in SD only | Linked to several old pages | TBA | 40 | Medium | Sprint 4 | Any one | Needs wifi access, Needs a browser and Can be accessed using devices such as PC, laptop and smart phones | It will linked to admission page consisting form to apply for admission in SD only | Not Done

## Rough
Product Backlog
ID | Theme | As a | I want … | So that… | Notes | Priority | Sprint | Status
1 | Static | Visitor | all the courses name with the short description | student can come to know about course detail. |  |  |  | Not Done
2 | Static | Visitor | all the facility name with their qualification | anyone can come to know about the facility knowledge and experience level |  |  |  | Not Done
| Dynamic | Student | self assessment page | student can check their knoweldge on specified field
4 | Dynamic | Visitor | FAQ option in the webpage | anyone can ask queries related to this course. |  |  |  | Not Done
5 | Static | Visitor | some major project details with a short description | anyone can know more about the SD student project work |  |  |  | Not Done
6 | Static | Visitor | events page where we can store the event held | anyone can come to know about the different type of events held by the SD Course members |  |  |  | Not Done
7 | Static | Student | grading criteria system | no one has any query related to the criteria of getting marks |  |  |  | Not Done
8 | Dynamic | NewComer | admission inquiry page | newcomer can check their eligibility for getting admission in SD course |  |  |  | Not Done
9 | Dynamic | Visitor | testimonial slides | support the SD credibility and level of expertise |  |  |  | Not Done
10 | Dynamic | Student | CGPA Calculator | any student can calculate their cgpa according to their marks |  |  |  | Not Done
11 | Static | Visitor | Gallery | anyone can see the pictures of the events photos, group photos, achievement photos, and many more. |  |  |  | Not Done
12 | Dynamic | Visitor | to give the details about the laptop features and also provide link for website for buying laptop | it is easier for the new student to buy a laptop for this course |  |  |  | Not Done
13 | Static | Visitor | all the companies name that hires the student of Sd course | visitors can guess the placement rate |  |  |  | Not Done
14 | Dynamic | Visitor | an appointment page | that anyone can take the appointment from teachers by sending a short message |  |  |  | Not Done
16 | Dynamic | Student | a calendar for upcoming events and Holidays | student can check events and holidays by visiting on the site |  |  |  | Not Done
17 | Dynamic | Student | mentor/ mentee detail | interns can check their mentor/ mentee detail and ask about their queries. |  |  |  | Not Done
18 | Dynamic | Visitor | a feedback form | visitor can give their feedback or can rate the website |  |  |  | Not Done