## Sprint1
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART (Team 1)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
1. As a student I want to see all the subject in the SD Course with their short description so that I can see all the subjects of SD course in each semester separately | 13 |  | Done | [6 empty] | 5
Create a web page |  | MOHIT | Done | 10 | 10 | 0 | 0 | 0 | 0 | 0
Display all the subjects of SD course in each semester seperately |  | ADITYA | Done | 30 | 10 | 10 | 0 | 10 | 0 | 0
Make a query form |  | AYUSH | Done | 40 | 10 | 10 | 0 | 10 | 10 | 0
put all information in tabular form |  | ASHFAK | Done | 40 | 10 | 10 | 10 | 0 | 10 | 0
2. As a student I want all the faculty details page so that I can see each faculty name along with their photo, skills, area of expertise | 13 |  | Done | [6 empty] | 5
Create a new web page |  | RUCHI | Done | 20 | 10 | 0 | 0 | 0 | 0 | 0
display the images, skills and area of expertise of faculty members |  | ASHFAK | Done | 40 | 0 | 10 | 10 | 10 | 10 | 0
put all information in tabular form |  | TANMOY | Done | 20 | 10 | 10 | 10 | 10 | 15 | 0
Make an appointment page |  | AYUSH | Done | 20 |  |  | 10 | 10
3 As a student I want grading criteria system so that I can come to know about the grading criteria of SD course | 13 |  | Done
describe the grading criteria of SD course through pie chart |  | MOHIT | Done | 50 | 0 | 10 | 20 | 10 | 15 | 0
table containing all the percentage, grade and gpa |  | ASHFAK | Done | 0 | 0 | 0 | 0 | 0 | 10
TOTAL |  |  |  | 270 | 60 | 60 | 60 | 60 | 70 | 10

## Sprint2
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
4. As a student I want FAQ option in the webpage so that I can ask about the queries related to this course | 40 |  | Done | [6 empty] | 5
Create a new web page |  | Aditya | Done | 15 | 15 | 0 | 0 | 0 | 0 | 0
Make an enquiry form |  | Ruchi | Done | 30 | 0 | 10 | 10 | 0 | 10 | 0
make an interactive chat option |  | Ashfak | Done | 50 | 0 | 10 | 20 | 10 | 10 | 0
Add some default question |  | Ruchi | Done | 30 | 20 | 10 | 0 | 0 | 0 | 0
Connect to email |  | Ashfak | Done | 20 | 0 | 0 | 0 | 10 | 10 | 0
5 As a Student I want gallery page so that I can see the images like all the events photos, group photos, achievement photos. | 40 |  | Done | [6 empty] | 5
craete a new web page |  | Mohit | Done | 25 | 15 | 0 | 0 | 0 | 10 | 0
Add photos |  | Tanmoy Joy | Done | 40 | 10 | 10 | 10 | 10 | 0 | 0
All the images are in slide show format |  | Mohit | Done | 30 | 0 | 0 | 10 | 10 | 10 | 0
Use animation |  | Ayush | Done | 50 | 0 | 20 | 10 | 20 | 10 | 0
TOTAL |  |  |  | 290 | 60 | 60 | 60 | 60 | 60 | 10

## Sprint 3
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
6. As a student I want some major project details with a short description so that I can see the different major project of difference subject along with their image or video and also the project creator and faculty who guided the projects | 40 |  | Not Done | [6 empty] | 5
Add some project detail in images or video format |  | Ayush |  | 30 | 10 | 5 | 5 | 5 | 5 | 0
Add some description about the project |  | Tanmoy |  | 40 | 10 | 10 | 5 | 10 | 5 | 0
7 As a Student I want testimonials slide so that I can see the name, image and testimonials of SD faculty and students | 13 |  | Not Done | [6 empty] | 5
Add photos , names |  | Tanmoy |  | 40 | 10 | 5 | 10 | 10 | 5 | 0
All the images are in slide show format |  | Ruchi |  | 30 | 10 | 5 | 10 | 5 | 5 | 0
Use animation |  | Aditya |  | 40 | 10 | 10 | 5 | 10 | 5 | 0
8. As a student I want CGPA Calculator so that I can enter my marks and calculate the CGPA. |  |  | Not Done | [6 empty] | 5
create a form to accept marks |  | Mohit |  | 20 | 10 | 10 | 10 | 0 | 0 | 0
make a calculator |  | Ruchi |  | 50 | 0 | 10 | 10 | 10 | 20 | 0
write js code |  | Ashfak |  | 40 | 0 | 5 | 5 | 10 | 10 | 0
TOTAL |  |  |  | 290 | 60 | 60 | 60 | 60 | 55 | 15

## Sprint 4
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
As a student I want a user friendly so that I can browse through the website with ease and comfort and understand all the aspects and features | 60
Remove all the containers, backgroung images and unnecessary texts |  | Tanmoy | Done | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Put facaulty details in a card form |  | Mohit | Done | 60 | 10 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 0 | 0 | 2
Change course detailes layout according to the new UI |  | Ruchi | Done | 40 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Insert Default questions and answers in FAQ. |  | Aditya | Done | 30 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 2
Put the testimonials in t to right to lrft animation |  | Ayush | Done | 40 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 2
Make the galarry page according to the UI |  | Ashfak | Done | 40 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 0 | 0 | 2
Make the event page according to the UI |  | Mohit | Done | 40 | 0 | 0 | 0 | 10 | 10 | 20 | 0 | 0 | 0 | 0 | 2
Add navigation bar with dropdown menu and useful links whuch remains fixed |  | Ashfak | Done | 30 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Make the academic page according to the new UI |  | Ruchi | Done | 40 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Make the footer with all the links mentioned in the UI |  | Ayush | Done | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 2
Make home page as per the UI decided by the team |  | Ashfak | Done | 60 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 2
TOTAL |  |  |  | 425 | 60 | 55 | 50 | 50 | 50 | 50 | 50 | 40 | 10 | 0 | 22

## Sprint 5
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
10 As a Student I want mentor/ mentee detail so that I can see the list of mentor or mentee of each semester and their names. | 13
create a new web page |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0
Add details about mentor/ mentee |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
add option for query |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
connect to mail |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
11.As a Student I want an appointment page so that I can request for an appointment to the Sd faculty through mail
create a new web page |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0
Add option for appointment |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
connect to mail |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 180 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 6
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
12. As a student I want project details sa that I can see some projects that has been done in sd programme. | 40
Create a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add images or video |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Add event details |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0
Add a form to request for hosting an event |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
connect to mail |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
13. As a Student I want self assessment page so that I can check my knowledge in different subjects through some basic MCQ of 12th standard and some Technical/General knowledge based questions | 13
craete a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add subjects |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Add quiz in google form |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
16. As a student I want a feedback form so that I can give comment or feedback and which will be mailed to all faculty members | 40
Create a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add a feedback form |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
connect to mail |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 240 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 7
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (min.) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
14. As a student I want to know about the laptop requirements so that I can know the minimum laptop requirements along with some suggestions of laptops we might like to buy. | 40
Create a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add laptop detail |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0
Add link to buy laptop |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0
Add some suggestion |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
15 As a student I want Calendar so that I can see the list of all the events and holidays | 13
craete a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add calendar |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Add upcoming holiday and events |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
16 As a Student I want all the companies name that hires the student of Sd course so that I can come to know the name of all the majoy IT companies that often comes to offer internship | 13
craete a new web page |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add companies logo |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Add company link |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Add placed student photos |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 280 | 0 | 0 | 0 | 0 | 0 | 0