## Sprint 1
TO-DO LIST
Task | Status | Priority | Due Date | Assignee | Notes
1..Create a web page of course detail | Completed | Medium | 2020-09-08 | MOHIT | Created a web page
Display all the subjects of SD course in each semester seperately | Completed | Medium | 2020-09-11 | ADITYA | Shows all the subjects of SD course in each semester seperately
describe short detail about all the course subject seperately | Completed | Medium | 2020-09-11 | ASHFAK | Mentioned the detail of all the courses
put all information in tabular form | Completed | Medium | 2020-09-11 | AYUSH | details are mentioned in tabular form
2..Create a new web page | Completed | Medium | 2020-09-08 | RUCHI | It will take to another page
display the images, skills and area of expertise of faculty members | Completed | Medium | 2020-09-11 | ASHFAK | where each faculty name along with their photo, qualification, area of experties
put all information in tabular form | Completed | Low | 2020-09-11 | TANMOY | And also a button to request for an appointment will be added in a card for each faculty
3..Create a new web page | Done | Medium | 2020-09-09 | ADITYA | It will take to a page consisting table .
describe the grading criteria of SD course | Completed | Low | 2020-09-11 | MOHIT | It will show the unique grading system of SD course
CLICK HERE TO CREATE IN SMARTSHEET

## Sprint 2
TO-DO LIST
Task | Status | Priority | Due Date | Assignee | Notes
1..Create a new web page | Done | Medium | 2020-09-15 | Aditya | Page should contains header and footer similar to pervoius pages
Make an enquiry form | Done | High | 2020-09-18 | Ruchi | A form that accepts queries
make an interactive chat option | Done | Medium | 2020-09-17 | Ashfak | It will lead to a page asking with lots of questions about what kind of quairy
Add some default question | Done | Low | 2020-09-16 | Ruchi | Insert some frequently asked questions
Connect to email | Done | High | 2020-09-18 | Ashfak | send query via email
2..craete a new web page | Done | Medium | 2020-09-15 | Mohit | Page should contains header and footer similar to pervoius pages
Add photos | Done | Medium | 2020-09-16 | Tanmoy Joy | it will lead to a page filled with only the images like all the events photos, group photos, achievement photos
All the images are in slide show format | Done | Medium | 2020-09-18 | Mohit | Images are shown in slide format
Use animation | Done | High | 2020-09-18 | Ayush | Use some animation in the slide

## Sprint 3
TO-DO LIST
Task | Status | Priority | Due Date | Assignee | Notes
Add some project detail in images or video format | Done | Medium | 2020-09-22 | Ayush | It will take you to a page where different major project along with their video
Add some description about the project | Done | Low | 2020-09-23 | Tanmoy | page should contains some description about the project, creator and faculty who guided the projects
Add photos , names | Done | Medium | 2020-09-22 | Tanmoy | page should including name, image and testimonils of SD faculty and students
All the images are in slide show format | Done | Medium | 2020-09-23 | Ruchi | Images are shown in slide format
Use animation | Done | High | 2020-09-24 | Aditya | Use some animation in the slide
create a form to accept marks | Done | Medium | 2020-09-24 | Mohit | It will lead to a page which will accepts the marks(numeric) and then calculate the CGPA.
make a calculator | Done | Medium | 2020-09-25 | Ruchi | calculator should look simple and interactive and contains proper size of input and output box
write js code | Done | High | 2020-09-25 | Ashfak | Use js code to calculate the CGPA

## Sprint4
TO-DO LIST
Task | Status | Priority | Due Date | Assignee | Notes
Remove all the containers, backgroung images and unnecessary texts | Done | Medium | 2020-09-30 | Tanmoy | It will remove all the extra text and containers from the different web pages. Of UI.
Put facaulty details in a card form | Done | Low | 2020-10-01 | Mohit | It will take you to new page where you can see about the sd faculty.
Change course detailes layout according to the new UI | Done | Medium | 2020-10-02 | Ruchi | It will change course detail and take you in the academic page to show about course.
Insert Default questions and answers in FAQ. | Done | Medium | 2020-10-01 | Aditya | page should including default questions and answsers related to website.
Put the testimonials in t to right to lrft animation | Done | Medium | 2020-10-07 | Ayush | testimonials are shown in slide format
Make the galarry page according to the UI | Done | High | 2020-10-06 | Ashfak | Create a new page and insert some images in a collarge format.
Make the event page according to the UI | Done | Medium | 2020-10-08 | Mohit | creat a new page with a list of events and calender.
Add navigation bar with dropdown menu and useful links whuch remains fixed | Done | Medium | 2020-10-05 | Ashfak | Create header as the navigation bar in the php code which give permission to show all the content of header without copying the header on every page.
Make the academic page according to the new UI | Done | Medium | 2020-09-25 | Ruchi | Academic create with new ui which tell about sd and sd course(subject) that we going to read in sd.
Make the footer with different link and text which may be related todifferent web pages. | Done | High | 2020-09-25 | Ayush | Footer in the php code which give permission to show all the content of footer without copying the footer on every page.
Make home page as per the UI decided by the team | Done | High | 2020-10-09 | Ashfak | Create a first page of the website according to ui.