## Sprint 1
TO-DO LIST
Task | Status | Priority | Due Date | Assignee | Notes
1..Create a web page of course detail | Completed | Medium | 2020-09-08 | MOHIT | Created a web page
Display all the subjects of SD course in each semester seperately | Completed | Medium | 2020-09-11 | ADITYA | Shows all the subjects of SD course in each semester seperately
describe short detail about all the course subject seperately | Completed | Medium | 2020-09-11 | ASHFAK | Mentioned the detail of all the courses
put all information in tabular form | Completed | Medium | 2020-09-11 | AYUSH | details are mentioned in tabular form
2..Create a new web page | Completed | Medium | 2020-09-08 | RUCHI | It will take to another page
display the images, skills and area of expertise of faculty members | Completed | Medium | 2020-09-11 | ASHFAK | where each faculty name along with their photo, qualification, area of experties
put all information in tabular form | Completed | Low | 2020-09-11 | TANMOY | And also a button to request for an appointment will be added in a card for each faculty
3..Create a new web page | Completed | Medium | 2020-09-09 | ADITYA | It will take to a page consisting table .
describe the grading criteria of SD course | Completed | Low | 2020-09-11 | MOHIT | It will show the unique grading system of SD course
CLICK HERE TO CREATE IN SMARTSHEET

## Sprint 2
TO-DO LIST
Task | Status | Priority | Due Date | Assignee | Notes
1..Create a new web page | Working | Medium | 2020-09-15 | Aditya | Page should contains header and footer similar to pervoius pages
Make an enquiry form | Working | High | 2020-09-18 | Ruchi | A form that accepts queries
make an interactive chat option | Working | Medium | 2020-09-17 | Ashfak | It will lead to a page asking with lots of questions about what kind of quairy
Add some default question | Working | Low | 2020-09-16 | Ruchi | Insert some frequently asked questions
Connect to email | Working | High | 2020-09-18 | Ashfak | send query via email
2..craete a new web page | Working | Medium | 2020-09-15 | Mohit | Page should contains header and footer similar to pervoius pages
Add photos | Working | Medium | 2020-09-16 | Tanmoy Joy | it will lead to a page filled with only the images like all the events photos, group photos, achievement photos
All the images are in slide show format | Working | Medium | 2020-09-18 | Mohit | Images are shown in slide format
Use animation | Working | High | 2020-09-18 | Ayush | Use some animation in the slide

## Disclaimer
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.